## Sheet1
Midwestern Contractors (MW) Internal Audit for Project Management (PM)
ECMW Auditor: |  | Status Key:
Site Assessment Date: |  |  | C = Compliant |  |  | O = Opportunity for Change
QA or QC?: |  |  | N= Non-Compliant
Process Owner: |  |  | I = Area for Improvement
Question: | Document(s) Reference: |  |  | Status | Comments
Estimating Phase:
1.1 Has customer information been documented? | ECMW-QMS-005
1.2 Has a site visit been arranged? | ECMW-QMS-005
1.3 Has a scope of work been documented? | ECMW-QMS-005
1.4 Have the project locations been documented? | ECMW-QMS-005
1.5 Have drawings and bid documents been documented? | ECMW-QMS-005
1.6 Have Contract terms been defined? | ECMW-QMS-005
1.7 Any special insurance requirements? | ECMW-QMS-005
1.8 Legal review? | ECMW-QMS-005
1.9 Material take-off performed? | ECMW-QMS-005
1.10 Equipment take-off performed? | ECMW-QMS-005
1.11 Labor take-off performed? | ECMW-QMS-005
1.12 Was subcontractor work identified and docuemented? | ECMW-QMS-005
1.13 Was communications documented? | ECMW-QMS-005
1.14 Was document ECMW-QCD-003 completed for this phase? | ECMW-QMS-005
2.0 Pre-Planning Phase
2.1 Was a written and signed agreement made with customer? | ECMW-QMS-005
2.1 Has the PM documented terms of payment and retainage? | ECMW-QMS-005
2.3 Project Schedule? Budget? Job Number? Invoice Schedule? | ECMW-QMS-005
2.4 Have materials been ordered and documented? | ECMW-QMS-005
2.5 Equipment been requisitioned? | ECMW-QMS-005
2.6 Labor been requisitioned? | ECMW-QMS-005
2.6.1 Labor Schedule set? | ECMW-QMS-005
2.7 Subcontractor agreement made and signed including insurance requirements? | ECMW-QMS-005
2.7.1 Subcontractor budget? Work schedule? Invoice Schedule? | ECMW-QMS-005
2.7.2 Issue P.O. to subcontractor? | ECMW-QMS-005
2.8 Close-out requirements documented? | ECMW-QMS-005
2.9 Attend pre-job with union rep? | ECMW-QMS-005
2.10 All permits and licenses in place? | ECMW-QMS-005
2.11 Hazardous and Non-Hazardous waste addressed? | ECMW-QMS-005
2.12 Documents ECMW-QCD-003 and ECMW-QCD-007 completed for this phase? | ECMW-QMS-005
3.0 Project Management Phase:
3.1 Archived all critical documentation according to checklist MW-QCD-008? | ECMW-QMS-005
3.2 Project Schedule updated? | ECMW-QMS-005
3.3 Invoices prepared and sent? | ECMW-QMS-005
3.4 Subcontractor and Vendor invoices compiled and approved? | ECMW-QMS-005
3.5 Document singed Change Orders? | ECMW-QMS-005
3.6 Reviewed and documented daily time sheets? | ECMW-QMS-005
3.7 Review material shipments for accuracy? | ECMW-QMS-005
3.8 Was checklist ECMW-QCD-003 completed for this phase? | ECMW-QMS-005
4.0 Project Closure Phase:
4.1 Punch List/Closeout made and reviewed with foreman/supervisor? | ECMW-QMS-005
4.2 Review results with senior management? | ECMW-QMS-005
4.2.1 Profit/Loss? | ECMW-QMS-005
4.2.2 Customer Satisfaction? | ECMW-QMS-005
4.2.3 Safety? | ECMW-QMS-005
4.2.4 Field employee performance? | ECMW-QMS-005
4.2.5 Subcontractor and Supplier performance? | ECMW-QMS-005
4.2.6 Job estimate compared to actual? | ECMW-QMS-005
4.3 Were final lien waivers in before payment? | ECMW-QMS-005
4.4 Obtain final retainage payments? | ECMW-QMS-005
4.5 Complete ECMW-QCD-003 for this phase? | ECMW-QMS-005