## Sheet1
Electric Conduit Construction (EC) Internal Audit for Project Management (PM)
ECMW Auditor: |  | Status Key:
Site Assessment Date: |  |  | C = Compliant |  |  | O = Opportunity for Change
QA or QC?: |  |  | N= Non-Compliant
Process Owner: |  |  | I = Area for Improvement
Question: |  |  |  | Job Status | Comments
Estimating Phase:
1.1 Has customer information been documented? | Yes No N/A
1.2 Has a site visit been arranged? | Yes No N/A
1.3 Has a scope of work been documented? | Yes No N/A
1.4 Have the project locations been documented? | Yes No N/A
1.5 Have drawings and bid documents been documented? | Yes No N/A
1.6 Have Contract terms been defined? | Yes No N/A
1.7 Any special insurance requirements? | Yes No N/A
1.8 Legal review? | Yes No N/A
1.8.1 If EC is subcontractor, legal review?
1.9 Material take-off performed? | Yes No N/A
1.10 Equipment take-off performed? | Yes No N/A
1.11 Labor take-off performed? | Yes No N/A
1.12 Was subcontractor work identified and documented? | Yes No N/A
1.12.1 Ensure subcontractor has met insurance and other requirements? | Yes No N/A
1.12.2 Contact Subcontractor for site visit? | Yes No N/A
1.13 Was communications documented? | Yes No N/A
2.0 Pre-Project Planning
2.1 Was a written and signed agreement made with customer? | Yes No N/A
2.1 Has the PM documented terms of payment and retainage? Consulted with legal? | Yes No N/A
2.3 Project Schedule? Budget? Job Number? Invoice Schedule? | Yes No N/A
2.4 Understand and review special requests with customer and applicable company personnel? | Yes No N/A
2.5 Consult with warehouse on ordering material, tools and equipment? | Yes No N/A
2.7 Subcontractor agreement made and signed including insurance requirements? | Yes No N/A
2.7.1 Subcontractor budget? Work schedule? Invoice Schedule? | Yes No N/A
2.7.2 Issue P.O. to subcontractor? | Yes No N/A
2.7.3 refer to subcontractor checklist ECMW-QCD-007 | Yes No N/A
2.8 Close-out requirements documented? | Yes No N/A
2.9 Coordinate with safety coordinator on safety issues? | Yes No N/A
2.10 All permits and licenses in place? | Yes No N/A
2.11 Hazardous and Non-Hazardous waste addressed? | Yes No N/A
3.0 Project Management Phase:
3.1 Collect all critical documentation, photos? Insure foreman is uploading to job file?
3.2 Project Schedule updated? | Yes No N/A
3.3 Invoices prepared and sent? | Yes No N/A
3.4 Subcontractor and Vendor invoices compiled and approved? | Yes No N/A
3.5 Documentand sign Change Orders? | Yes No N/A
3.6 Reviewed and documented daily time sheets? | Yes No N/A
3.7 Review material shipments for accuracy? | Yes No N/A
3.8 Ensure through accounts receivable timely customer payments throughout job? | Yes No N/A
4.0 Project Close-Out:
4.1 Punch List/Closeout made and reviewed with foreman/supervisor? | Yes No N/A
4.2 Review results with senior management? | Yes No N/A
4.2.1 Profit/Loss? | Yes No N/A
4.2.2 Customer Satisfaction? | Yes No N/A
4.2.3 Safety? | Yes No N/A
4.3 Were final lien waivers in before payment? | Yes No N/A
4.4 Obtain final retainage payments? | Yes No N/A